## Sheet1
| Project Name | Project Description | STATUS | Anticipated Project Cost | e-Builder Current Commitments | eBuilder Project Name | Notes
SANTA MONICA
(Click on school name for school specific facility projects webpage)
Edison Language Academy
BB | New Elementary School | Construct/Replace Elementary School | Completed | 62738388 |  | - | Not in eBuilder
|  | Land Acquisition |  | 3540041 |  | - | Not in eBuilder
|  | Relocatables |  | 8248 |  | - | Not in eBuilder
|  | Temporary Preschool at Rogers |  | 9430 |  | - | Not in eBuilder
SMS | Furniture, Fixtures & Equipment (FFE) | 21st century classroom furniture upgrade | Completed | 800000 | 73704.06 | Edison ES FF&E Project (SMS)
SMS | Safety & Security | Adding cameras, raptor and other safety upgrades | Completed | 300000 | 481375.9 | Edison ES Safety & Security Project (SMS)
SMS | Campus Assessment & Planning | Master Planning process | Completed | 90000 | 137478.61 | Edison ES Elementary School Assessment (SMS)
SMS | Edison ES HVAC Improvements | Installation of new HVAC controls that will optimize the conditioning of interior spaces and the flow of outside air. | Completed | 168191 | 283511.84 | Edison ES HVAC Improvements (SMS)
ES | Solar Project | Solar Project | Completed |  | 442030.61 | Edison ES Solar Project (ES) | In eBuilder but not in the original spreadsheet
SMS | Edison ES Safety & Security Project - PA/Clock Replacement Project | Replacement of analogue PA/Clock system with a new IP based PA/Clock system including digital messaging. | Completed | 72290 | 74948.96 | Edison ES Safety & Security Project - PA/Clock Replacement Project (SMS)
Franklin Elementary School
ES | Modernization & HVAC | Window, Paint, Floor and Door Project, HVAC, Fire Alarm & ADA | Completed | 8671209 | 8283888.11 | Franklin ES WFPD & HVAC Project (ES)
SMS | Furniture, Fixtures & Equipment (FFE) | 21st century classroom furniture upgrade | Completed | 900000 | 734541.52 | Franklin ES FF&E Project (SMS)
SMS | Safety & Security | Adding cameras, raptor and other safety upgrades | Completed | 300000 | 409818.8 | Franklin ES Safety & Security Project (SMS)
SMS | Campus Assessment & Planning | Master Planning process | Completed | 200000 | 908065.99 | Franklin ES Elementary School Assessment (SMS)
SMS | Campus Plan | Develop new campus plan | Completed | 1578785 |  |  | Not in eBuilder
ES | Franklin ES Roofing Replacement Project | Replacement of roofs on Buildings A and F. | Completed | 1289068 | 1291538.58 | Franklin ES Roofing Replacement Project (ES)
SMS | Franklin ES Safety & Security Project -PA/Clock Replacement Project | Replacement of analogue PA/Clock system with a new IP based PA/Clock system including digital messaging. | Completed | 637351 | 0 | Franklin ES Safety & Security Project - PA/Clock Replacement Project (SMS)
SMS | Maker Space Building and Field / Front Fence Project | Maker Space Building and Field / Front Fence Project | In Design |  | 1741194.8 | Franklin ES Maker Space Building and Field / Front Fence Project (SMS) | In eBuilder but not in the original spreadsheet
SMS | New Early Childhood Building | Construct TK/k classrooms, new field and relocate parking lot (design only) | In Design | 3687293 | 3969857.62 | Franklin ES Early Education Classrooms & Site Improvements Project (SMS)
QS | New Early Childhood Building (construction 6/2026) | Construct TK/k classrooms, new field and relocate parking lot (construction) | In DSA | TBD |  | Franklin ES Early Education Classrooms & Site Improvements Project (QS)
Grant Elementary School
BB | Main Entry Reconfiguration | Security upgrades to entry and main office | Completed | 548302 |  |  | Not in eBuilder
ES | Modernization | Window, Paint, Floor and Door Project | Completed | 2299681 | 2299680.3 | Grant ES WPFD Project (ES)
ES | HVAC & Fire Alarm | Upgrade HVAC, Electrical, Fire Alarm, & ADA (design only) | Completed | 303266 | 303266.09 | Grant ES HVAC & Electrical Project (ES)
SMS | HVAC & Fire Alarm | Upgrade HVAC, Electrical, Fire Alarm, & ADA (construction only) | Completed | 5000000 | 6303931.11 | Grant ES HVAC Project (SMS)
SMS | Furniture, Fixtures & Equipment (FFE) | 21st century classroom furniture upgrade | Completed | 800000 | 1029704.04 | Grant ES FF&E Project (SMS)
SMS | Safety & Security | Adding cameras, raptor and other safety upgrades | Completed | 300000 | 445825.97 | Grant ES Safety & Security Project (SMS)
SMS | Campus Assessment & Planning | Master Planning process | Completed | 200000 | 1695193.85 | Grant ES Elementary School Assessment (SMS)
SMS | TK Expansion and Modernization | Transform 4 classrooms into 3 transitional kindergarten classrooms (design only) | In Design | 3000000 | 6792087.22 | Grant ES Early Education Modernization Project (SMS)
SMS | Library Modernization | Renovate & expand the existing library & innovation classroom (design only) | In Design | 191050 | 12628316 | Grant ES Library Renovation Project (SMS)
SMS | New Classroom Building | Construct new classroom building with roof top learning garden (design only) | In Design | 2314060 | 29785227.28 | Grant ES Classroom Building Project (SMS)
QS | TK Expansion and Modernization | Transform 4 classrooms into 3 transitional kindergarten classrooms (construction only) | Completed |  | 7634.75 | Grant ES Early Education Modernization Project (QS)
QS | Library Modernization | Renovate & expand the existing library & innovation classroom (construction only) | Construction |  |  |  | eBuilder does not have a project with QS funding for the Grant ES Library Renovation Project.
QS | New Classroom Building | Construct new classroom building with roof top learning garden (construction only) | Construction |  | 83700 | Grant ES Classroom Building Project (QS)
McKinley Elementary School
BB | Entry and Main Office Reconfiguration | Security upgrades to entry and main office | Completed | 1371983 |  |  | Not in eBuilder
ES | Modernization & HVAC | Window, Paint, Floor and Door Project, HVAC, Fire Alarm & ADA | Completed | 10103157 | 10946357.08 | McKinley ES WFPD & HVAC Project (ES)
ES | Library Renovation Project (ES - WFP) | Library Renovation Project (ES - WFP) | Completed |  | 308987.81 | McKinley ES Library Renovation Project (ES - WFP) | In eBuilder but not in the original spreadsheet
SMS | Furniture, Fixtures & Equipment (FFE) | 21st century classroom furniture upgrade | Completed | 800000 | 947678.97 | McKinley ES FF&E Pilot Project (SMS)
SMS | Safety & Security | Adding cameras, raptor and other safety upgrades | Completed | 300000 | 438539.86 | McKinley ES Safety & Security Project (SMS)
SMS | Campus Assessment & Planning | Master Planning process | Completed | 200000 | 3068815.11 | McKinley ES Elementary School Assessment (SMS)
SMS | Safety & Security Project - PA/Clock Replacement Project | Replacement of analogue PA/Clock system with a new IP based PA/Clock system including digital messaging. | Completed | 657488 | 58292.31 | McKinley ES Safety & Security Project - PA/Clock Replacement Project (SMS)
SMS | Library Modernization Project (SMS) | Library Modernization Project (SMS) | Completed |  | 103630.91 | McKinley ES Library Modernization Project (SMS) | In eBuilder but not in the original spreadsheet
SMS | New Classroom Building and Administration | Construction of a new 8 classroom elementary school building and administration offices. | Construction | 37380000 | 36190034.93 | McKinley ES Administration and Early Elementary Building Project (SMS)
QS | New Classroom Building and Administration | Construction of a new 8 classroom elementary school building and administration offices. | Construction |  | 0 | McKinley ES Administration and Early Elementary Building Project (QS)
Will Rogers Learning Community
BB | Entry and Main Office Reconfiguration | Security upgrades to entry and main office | Completed | 397508 |  |  | Not in eBuilder
ES | Church Property | Demo, Parking Lot and Lawn | Completed | 653454 |  |  | Not in eBuilder
ES | Modernization | Window, Paint, Floor and Door & ADA upgrades | Completed | 6443448 | 6419766.18 | Will Rogers ES WPFD Project (ES)
ES | HVAC & Fire Alarm | Upgrade HVAC, Electrical, Fire Alarm, & ADA (design only) | Completed | 166564 | 166563.39 | Will Rogers ES HVAC & Electrical Project (ES)
ES | 16th Street Parking Lot | 16th Street Parking Lot | Completed |  | 651203.99 | Will Rogers ES 16th Street Parking Lot (ES) | In eBuilder but not in the original spreadsheet
SMS | HVAC & Fire Alarm | Upgrade HVAC, Electrical, Fire Alarm, & ADA (construction only) | Completed | 4000000 | 3822672.07 | Will Rogers ES HVAC Project (SMS)
SMS | HVAC Project - Mechanical Façade | HVAC Project - Mechanical Façade | Completed |  | 210915.62 | Will Rogers ES HVAC Project - Mechanical Facade (SMS) | In eBuilder but not in the original spreadsheet
SMS | Furniture, Fixtures & Equipment (FFE) | 21st century classroom furniture upgrade | Completed | 900000 | 1031335 | Will Rogers ES FF&E Pilot Project (SMS)
SMS | Safety & Security | Adding cameras, raptor and other safety upgrades | Completed | 250000 | 798671.65 | Will Rogers ES Safety & Security Project (SMS)
SMS | Campus Assessment & Planning | Master Planning process | Completed | 250000 | 2072058.32 | Will Rogers ES Elementary School Assessment (SMS)
SMS | Safety & Security Project - PA/Clock Replacement Project | Replacement of analogue PA/Clock system with a new IP based PA/Clock system including digital messaging. | Completed | 685876 | 0 | Will Rogers ES Safety & Security Project - PA/Clock Replacement Project (SMS) | Likley all cost for this project are included in the "Safety & Security Project"
SMS | Early Elementary Building Project | Construction of a new early learning classroom building and play field | Completed | 24780000 | 30796765.82 | Will Rogers ES Early Elementary Building Project (SMS)
QS | Early Elementary Building Project | Construction of a new early learning classroom building and play field | Completed |  | 21896.4 | Will Rogers ES Early Elementary Building Project (QS) | In eBuilder but not in the original spreadsheet
Roosevelt Elementary School
ES | Modernization | Window, Paint, Floor and Door, Fire Alarm & ADA upgrades | Completed | 4009467 | 3955441.75 | Roosevelt ES WPFD Project (ES)
ES | HVAC & Fire Alarm | Upgrade HVAC, & Electrical (design only) | Completed | 168137 | 168136.41 | Roosevelt ES HVAC & Electrical Project (ES)
SMS | HVAC & Fire Alarm | Upgrade HVAC, Electrical, Fire Alarm, & ADA (construction only) | Completed | 3500000 | 2338349.65 | Roosevelt ES HVAC Project (SMS)
SMS | Furniture, Fixtures & Equipment (FFE) | 21st century classroom furniture upgrade | Completed | 900000 | 924027.57 | Roosevelt ES FF&E Project (SMS)
SMS | Safety & Security | Adding cameras, raptor and other safety upgrades | Completed | 300000 | 295503.79 | Roosevelt ES Safety & Security Project (SMS)
SMS | Campus Assessment & Planning | Master Planning process | Completed | 200000 | 1016327.04 | Roosevelt ES Elementary School Assessment (SMS)
ES | Roofing Replacement Project | Replacement of roofs on Buildings A, B, C and E. | Completed | 1812158.37 | 1812158.37 | Roosevelt ES Roofing Replacement Project (ES)
SMS | Safety & Security Project - PA/Clock Replacement Project | Replacement of analogue PA/Clock system with a new IP based PA/Clock system including digital messaging. | Completed | 680791 | 224751.02 | Roosevelt ES Safety & Security Project - PA/Clock Replacement Project (SMS)
SMS | New Library and Early Childhood Building | Construct new library and early childhood classrooms (design only) | In Process | 4082950 | 37543747.98 | Roosevelt ES TK/K Classrooms and Library Building Project (SMS)
QS | New Library and Early Childhood Building | Construct new library and early childhood classrooms (desig only) | Construction |  | 892455.53 | Roosevelt ES TK/K Classrooms and Library Building Project (QS)
SMASH / Muir Elementary School
BB | Emergency Gas Piping Repair | Repaired/replaced gas lines | Completed | 108497 |  |  | Not in eBuilder
BB | Entry Gate Project | Security upgrade to entry gate | Completed | 106155 |  |  | Not in eBuilder
ES | Modernization | Window, Paint, Floor and Door, Fire Alarm & ADA upgrades (design) | Completed | 130489 | 130489.54 | SMASH/Muir ES WPFD Project (ES)
ES | HVAC | Upgrade HVAC, & Electrical (design only) | Completed | 250701 | 250701.22 | SMASH/Muir ES HVAC & Electrical Project (ES)
SMS | Modernization & HVAC | Upgrade HVAC, Electrical, Fire Alarm, & ADA (construction only) | Completed | 6500000 | 7370697.64 | SMASH/Muir ES WFP & HVAC Project (SMS)
SMS | Furniture, Fixtures & Equipment (FFE) | 21st century classroom furniture upgrade | Completed | 600000 | 1477416.12 | SMASH/Muir ES FF&E Project (SMS)
SMS | Safety & Security | Adding cameras, raptor and other safety upgrades | Completed | 250000 | 238790.16 | SMASH/Muir ES Safety & Security Project (SMS)
SMS | Campus Assessment & Planning | Master Planning process | Completed | 120000 | 230387.2 | SMASH/Muir ES Elementary School Assessment (SMS)
SMS | Safety & Security Project - PA/Clock Replacement Project | Replacement of analogue PA/Clock system with a new IP based PA/Clock system including digital messaging. | Completed | 680791 | 0 | SMASH/Muir ES Safety & Security Project - PA/Clock and Intrusion Alarm Replacement Project (SMS)
SMS | Water Intrusion Renovation | Reconstruct campus to be water proof and properly functioning | In Process | 4928466 | 67935872.54 | SMASH/Muir Water Intrusion Repair Project (SMS)
SMS | Innovation Lab and Administration Renovation | Renovate 2 classrooms into admin and admin into innovation lab (design only) | In Process | 1634550 |  |  | Not in eBuilder
QS | Innovation Lab and Administration Renovation | Renovate 2 classrooms into admin and admin into innovation lab (construction only) | Construction | 1634550 |  |  | Not in eBuilder
John Adams Middle School
BB | Field Warranty & Defects | Warranty for synthetic field purchased/installed by SMC | Completed | 349075 |  |  | Not in eBuilder
BB | New Construction & Modernization | New 80s wing & Main Office, Modernize Art & Principal's Office | Completed | 25852966 |  |  | Not in eBuilder
BB | Parking Lot | Construct new parking lot at 16th & Ocena Park | Completed | 804654 |  |  | Not in eBuilder
BB | Relocatables | Swing Space classrooms and tennis court restore | Completed | 743195 |  |  | Not in eBuilder
BB | Field Site Improvements | Green Fringe at Perimeter of Athletic Fields | Completed | 638509 |  |  | Not in eBuilder
ES & SMS | Performing Arts Center | Theater, Choir Room, & Performance Studio Construction | Completed | 44200000 | 43142626.35 | JAMS Performing Arts Complex (PAC) (ES) & (SMS) | $26,942,626.35 (ES); $16,200,000 (SMS)
ES | Gym Floor Repacement | Replace Gym Floor, modernize & ADA upgrades | Completed | 1272753 | 1261555.26 | JAMS Gym Floor Replacement (ES)
ES | Synthetic Turf Replacement | Replace synthetic turf on soccer, football & softball fields | Completed | 2318777 | 2312892.98 | JAMS Replace Synthetic Turf (ES)
ES | Solar | Solar | Completed |  | 11752 | JAMS Solar Project (ES) | In eBuilder but not in the original spreadsheet
ES | HVAC & Electrical Project - Phase 1 | Upgrade of HVAC & Electrical for 1/2 campus, Fire Alarm for all | Completed | 6201131 | 6429665.06 | JAMS HVAC & Electrical Project (ES)
SMS | HVAC & Electrical Project - Phase 2 | Upgrade of HVAC & Electrical for 1/2 campus, | Completed | 4390482 | 4441178.49 | JAMS HVAC Phase II (SMS)
SMS | Furniture, Fixtures & Equipment (FFE) | 21st century classroom furniture upgrade | Completed | 1500000 | 1436456.17 | JAMS FF&E Pilot Project (SMS)
SMS | Safety & Security | Adding cameras, raptor and other safety upgrades | Completed | 500000 | 415367.39 | JAMS Safety & Security Project (SMS)
SMS | Safety & Security Project - PA/Clock Replacement Project | Safety & Security Project - PA/Clock Replacement Project | Completed |  | 1389400.98 | JAMS - Security Cameras, PA/Clocks, & Intrusion Alarm Improvements Project (Safety & Security) (SMS)
SMS | Campus Assessment & Planning | Master Planning process | Completed | 200000 | 520747.01 | JAMS Middle School Assessment Project (SMS)
SMS | Marquee Replacement Project | Replace of the original marquee tower and sign. | Completed | 279431 | 404082.34 | JAMS Marquee Replacement Project (SMS)
ES | Roofing Replacement Project | Replace of roof on building J | Completed | 367892.34 | 370181.35 | JAMS Roofing Replacement Project (ES)
SMS | Linear Couryard | Linear Courtyard | Completed | - | 1469110.21 | JAMS Linear Courtyard (SMS) | In eBuilder but not in the original spreadsheet
SMS | Upgrades & Repairs | Upgrades & Repairs | Completed | - | 4070.06 | JAMS Upgrades & Repairs (SMS) | In eBuilder but not in the original spreadsheet
SMS | Library Renovation | Renovate the existing library with addition of outdoor learning space | In Process | 230835 | 4017135.38 | JAMS Library Renovation Project (SMS)
SMS | New STEM Building | Construct new STEM building (design only) includes gym renovation design | In Process | 2573672 | 8357487.46 | JAMS STEM Building Project (SMS)
QS | New STEM Building | Construct new STEM building (construction only) includes gym renovation design | Construction | 2573672 | 951559.76 | JAMS STEM Building Project (QS)
Lincoln Middle School
BB | New Building C & Site Improvements | New Library & Classroom Building (Pkg 2) | Completed | 28440463 |  |  | Not in eBuilder
BB | Modernization Building E | Main Building Classroom & Lab modernization (Pkg 1B) | Completed | 3155016 |  |  | Not in eBuilder
BB | Relocatables & Site Utilities | Swing Space Classrooms for construction (Pkg 1A) | Completed | 770068 |  |  | Not in eBuilder
ES | Athletic Field & Track | Replace Field & Track and Restroom Upgrade | Completed | 6675774 | 6658828.07 | Lincoln MS Athletic Track & Field Renovation (ES)
ES | Building G & K Upgrades | Modernize Special Education and other classrooms (design only) | Completed | 268641 | -524965.96 | Lincoln MS Bldg G & K Modernization Project (SMS)
ES | HVAC & Electrical Project | Upgrade HVAC, Electrical & Fire Alarm (design only) | Completed | 161844 | 161843.42 | Lincoln MS HVAC & Electrical Project (ES)
ES | Upgrade Project | Upgrade Project | Completed |  | 22405.95 | Lincoln MS Upgrade Project (ES) | In eBuilder but not in the original spreadsheet
SMS | HVAC & Electrical Project | Upgrade HVAC, Electrical & Fire Alarm (construction only) | Completed | 10000000 | 11816126.34 | Lincoln MS HVAC Project (SMS)
SMS | Furniture, Fixtures & Equipment (FFE) | 21st century classroom furniture upgrade | Completed | 1500000 | 1144427.66 | Lincoln MS FF&E Pilot Project (SMS)
SMS | Safety & Security | Adding cameras, raptor and other safety upgrades | Completed | 500000 | 397146.13 | Lincoln MS Safety & Security Project (SMS)
SMS | Safety & Security Project - PA/Clock Replacement Project | Replacement of analogue PA/Clock system with a new IP based PA/Clock system including digital messaging. | Completed |  | 366762.56 | Lincoln MS Safety & Security Project - PA/Clock Replacement Project (SMS) | In eBuilder but not in the original spreadsheet
SMS | Campus Assessment & Planning | Master Planning process | Completed | 300000 | 572242.82 | Lincoln MS Middle School Assessment Project (SMS)
ES | Roofing Replacement Project | Replace of roofs on Buildings D, E, G and H. | In Process | 1819511.19 | 1825488.67 | Lincoln MS Roofing Replacement Project (ES)
SMS | CDS Playground Modernization | CDS Playground Modernization | In Process |  | 39760 | Lincoln CDS Playground Modernization Project (SMS) | In eBuilder but not in the original spreadsheet
QS | CDS Playground Modernization | CDS Playground Modernization | In Process |  | 321652 | Lincoln CDS Playground Modernization Project (QS) | In eBuilder but not in the original spreadsheet
SMS | Renovation of Existing 500's Building | Modernize shops building to be 8th grade project-based learning hub | In Process | TBA | 19478157.26 | Lincoln MS 500's Building Modernization Project (SMS)
QS | Renovation of Existing 500's Building | Modernize shops building to be 8th grade project-based learning hub | Construction | TBA | 623858.45 | Lincoln MS 500's Building Modernization Project (QS)
Obama Center (formerly Olympic High School)
BB | Demolish Relocatables | Remove old portable classrooms | Completed | 51720 |  |  | Not in eBuilder
BB | Landscape Improvements | Improve upper yard after portables demolished | Completed | 105362 |  |  | Not in eBuilder
BB | Modernization | Improve majority of school | Completed | 12674069 |  |  | Not in eBuilder
ES | Modernization & HVAC | Window, Paint, Floor and Door, Fire Alarm, HVAC, ADA (except 4 clrms) | Completed | 5395308 | 5671445.22 | Obama HS WFPD & HVAC Project (ES)
ES | Project Based Learning Upgrades | Beginning design work for PBL | Completed | 7065 | 7065.35 | Obama HS Project Based Learning (ES)
SMS | Modernization & HVAC | Window, Paint, Floor and Door, Fire Alarm, HVAC, ADA (last 4 clrms) | Completed | 927904 | 951117.86 | Obama HS WPF & HVAC Project - Phase II (SMS)
SMS | Project Based Learning Upgrades | Completed design and planning | Completed | 7500000 | 288762.04 | Obama HS Project Based Learning (SMS)
SMS | Furniture, Fixtures & Equipment (FFE) | 21st century classroom furniture upgrade | Completed | 600000 | 80686.26 | Obama HS FF&E Project (SMS)
SMS | Safety & Security | Upgrading cameras, raptor and other safety upgrades | Completed | 6557 | 447856.94 | Obama HS Safety & Security Project (SMS)
SMS | Modernization | Modernization | In design |  | 367785 | Obama HS Modernization Project (SMS) | In eBuilder but not in the original spreadsheet
SMS | Mural Wall Preparation | Mural Wall Preparation | Completed |  | 191247.16 | Obama HS Campus Improvement Project - Mural Wall Preparation (SMS) | In eBuilder but not in the original spreadsheet
SMS | Preschool and Special Ed Modernization | Modernizing classrooms/playyards for Preschool and new SPED STATS program | In design |  | 63260 | Obama Center-Early Childhood/Special Ed Modernization Project (SMS) | In eBuilder but not in the original spreadsheet
QS | Preschool and Special Ed Modernization | Modernizing classrooms/playyards for Preschool and new SPED STATS program | In design |  | 255160.38 | Obama Center-Early Childhood/Special Ed Modernization Project (QS)
Washington CDS, PDLC & FIP
BB | Child Development Center Upgrades | Modernization of Preschools and areas for CDS | Completed | 1790058 |  |  | Not in eBuilder
BB | Washington South Facilities Building | Repair and Modernization for CDS & FIP | Completed | 449073 |  |  | Not in eBuilder
ES | Washington West Moderization | Window, Paint, Floor and Door, Fire Alarm, HVAC, ADA of CDS & PDLC | Completed | 1172974 | 1172973.63 | Washington West WFPD & HVAC Project (ES)
SMS | Washington West Moderization | Window, Paint, Floor and Door, Fire Alarm, HVAC, ADA of CDS & PDLC | Completed | 2410887 | 2396592.81 | Washington West WFP & HVAC Project (SMS)
SMS | Furniture, Fixtures & Equipment (FFE) | 21st century classroom furniture upgrade | Completed | 150000 | 248906.66 | Washington West FF&E Pilot Project (SMS)
SMS | Safety & Security | Adding cameras, raptor and other safety upgrades | Completed | 100000 | 550697.98 | Washington West Safety & Security Project (SMS)
SMS | Elementary School Campus Assessment | Elementary School Campus Assessment | Completed |  | 59743.61 | Washington West Elementary School Assessment (SMS) | In eBuilder but not in the original spreadsheet
ES | Washington West WPFD & HVAC Project | Installation of new HVAC controls that will optimize the conditioning of interior spaces and the flow of outside air. | Completed | 59744 |  |  | This likely corresponds to the Campus Assessment Project as the values are the same.
SANTA MONICA HIGH SCHOOL
BB | New Science & Technology Building | Innovation Building and site improvements | Completed | 93186883 |  |  | Not in eBuilder
ES | Campus Plan | Master Planning the full campus buildout | Completed | 4176020 | 4951874.24 | Samohi Campus Plan (ES)
ES | Campus Plan Review | Campus Plan Review | Completed |  | 527714.87 | Samohi Campus Plan Review (ES) | In eBuilder but not in the original spreadsheet
SMS | Campus Plan Review | Campus Plan Review | Completed |  | 954614.25 | Samohi Campus Plan Review (SMS) | In eBuilder but not in the original spreadsheet
ES & SMS | Construct Phases 1 & 2 | Discovery and Site work, plus added parking | Completed | 185000000 | 201900375.22 | Samohi Discovery Bldg (ES) & (SMS)
ES | Barnum Hall Repairs & Upgrades | Campus Plan upgrades for Barnum Hall | Completed | 1000000 | 499972.21 | Samohi Barnum Hall Repairs & Upgrades (ES)
SMS | Barnum Hall Repairs & Upgrades | Campus Plan upgrades for Barnum Hall | Completed |  | 804163 | Samohi Barnum Hall Repairs & Upgrades (SMS) | In eBuilder but not in the original spreadsheet
ES | Football Field & Track Lighting | Upgrade field lighting to LED & controls | Completed | 139671 | 140131.03 | Samohi Football Field & Track Lighting Replacement (ES)
ES | HVAC & Electrical Project | Upgrade HVAC in buildings in use for 10+ years | Completed | 8962188 | 9801662.21 | Samohi HVAC & Electrical Project (ES)
ES | Roofing Replacement Project | Roofing Replacement Project | Completed |  | 492088.17 | Samohi Roofing Replacement Project (ES) | In eBuilder but not in the original spreadsheet
SMS | Roofing Replacement Project | Roofing Replacement Project | Completed |  | 26200 | Samohi Roofing Replacement Project (SMS) | In eBuilder but not in the original spreadsheet
ES | Interim Repairs/Upgrades | Various small projects needed for continued use of campus during SCP | Completed | 2173877 | 1502571.63 | Samohi Interim Repairs & Upgrades (Band-Aids) (ES)
SMS | Interim Repairs/Upgrades | Various small projects needed for continued use of campus during SCP | Completed |  | 5281805.88 | Samohi Interim Repairs & Upgrades (SMS) | In eBuilder but not in the original spreadsheet
SMS | Athletic Field Replacement | New synthetic turf carpet for football field | Completed | 855972 | 971290.85 | Samohi Athletic Field Replacement (SMS)
ES | Interim Softball Field | Adding Softball Field to Sealy Field and other upgrades | Completed | 4349925 | 4340758.2 | Samohi Sealy Field Lighting - Softball Field (ES)
ES | Science Quad Synthetic Turf | Upgrade science quad for us during construction | Completed | 113067 | 113066.65 | Samohi Science Quad Artificial Turf Project (ES)
ES | Path of Travel Upgrades | Adding stairs & ramps to science quad | Completed | 113067 | 66037.24 | Samohi Path of Travel Upgrade Project and Stairs-Ramp Near 7th-Michigan (ES)
ES | Solar Project | Adding photovoltaic panels to Innovation & battery backup | Completed | 1500000 | 1019532.03 | Samohi Solar Project (ES)
SMS | Furniture, Fixtures & Equipment (FFE) | 21st century classroom furniture upgrade | Completed | 2000000 | 207099.16 | Samohi FF&E Project (SMS)
ES | Safety & Security | Adding cameras, raptor and other safety upgrades | Completed | 6000000 | 3450 | Samohi Safety & Security Project (ES) | In eBuilder but not in the original spreadsheet
SMS | Safety & Security | Adding cameras, raptor and other safety upgrades | Completed |  | 916330.37 | Samohi Safety & Security Project (SMS)
SMS | Utility Infrastructure | part of Safety & Security | Completed | 750000 | 212409.62 | Samohi Utility Infrastructure - Safety & Security Project (SMS)
SMS | English, Business and Art Gallery | Installing transformer in English, repurposing Business and Creating Art Gallery | Completed | 4192998 | 4192997.83 | Samohi Interim Repairs & Upgrades - Misc. Improv. Ph 2 - Business & Art Gallery Repurpose Project (SMS)
SMS | Exploration and Gold Gym | New academic Building and Gold Gym to replace South Gym | In Progress | 127213000 | 22618947.65 | Samohi Phase III (SMS)
SMS | Exploration and Gold Gym | New academic Building and Gold Gym to replace South Gym | In Progress |  | 154102219.29 | Samohi Phase III - Exploration Building and Gymnasium (SMS) | Ashraf had this project separated. Not sure why.
SMS | North Gym Access Controls | Installing electronic access controls | Completed | 130607 |  |  | Not in eBuilder
SMS | Phase 4a English Building Renovation | Renovation reuse of existing building to accommodate Samohi Administration | On Hold | 3000320 | 3470629.48 | Samohi Administration Building Modernization Project (SMS)
SMS | Phase 4b New Student Center/Student Services | Replace business building with new student center/student services building (design only) | In Process | TBA | 156954 | Samohi Student Services Building (Phase 4A) Project (QS)
QS | Phase 4b New Student Center/Student Services | Replace business building with new student center/student services building (construction only)) | In Process | TBA | 4404188 | Samohi Student Services Building (Phase 4A) Project (SMS)
SMS | Infant Toddler Center | Infant Toddler Center |  |  | 204187.18 | Samohi Infant Toddler Center Project (SMS) | In eBuilder but not in the original spreadsheet
SMS | House Office | House Office | In Process |  | 595658.98 | Samohi House Office Project (SMS) | In eBuilder but not in the original spreadsheet
MALIBU
Webster Elementary School
BB | Fire Alarm Replacement | Replace Fire Alarm - Safety & Security | Completed | 467350 |  |  | Not in eBuilder
BB | Drop-off & Parking Lot Reconfiguration | Redesign the lower + mid parking lots and drop off areas - Safety | Completed | 5131262 |  |  | Not in eBuilder
ES | Modernization | Window, Paint, Floor and Door & ADA upgrades | Completed | 4005157 | 4346986.5 | Webster ES WPFD Project (ES)
M | Modernization | Window, Paint, Floor and Door & ADA upgrades | Completed |  | 13034.14 | Webster ES WPFD Project (M) | In eBuilder but not in the original spreadsheet
ES | HVAC | Upgrade HVAC, & Electrical (design only) | Completed | 244341 | 244341.35 | Webster ES HVAC & Electrical Project (ES)
M | HVAC & Electrical | Upgrade HVAC, Electrical (construction only) | Completed | 2506609 | 2461468.65 | Webster ES HVAC Project (M)
M | Furniture, Fixtures & Equipment (FFE) | 21st century classroom furniture upgrade | Completed | 600000 | 692498.57 | Webster ES FF&E Project (M)
M | Safety & Security | Adding cameras, raptor and other safety upgrades | Completed | 300000 | 515900.13 | Webster ES Safety & Security Project (M)
M | Sewer Connection | Connection to Malibu Sewage Treatment Plant | Postponed | 500000 |  |  | Not in eBuilder
M | Campus Assessment & Planning | Master Planning process | In Process | 280400 | 139625 | Webster ES Elementary School Campus Assessment (M)
M | Alternative Power | Alternative Power | In Process |  | 295543 | Webster ES Alternative Power Project (M) | In eBuilder but not in the original spreadsheet
Malibu Elementary School (formerly Point Dume Science School)
BB | Gas Line & Furnace Replacement | Repairs gas lines and updates heating system | Completed | 1018510 |  |  | Not in eBuilder
BB | Wastewater Treatment | Repair of Septic System | Completed | 110066 |  |  | Not in eBuilder
ES | Modernization & HVAC | Window, Paint, Floor and Door & Fire Alarm, HVAC, ADA upgrades | Completed | 5525540 | 5781555.61 | Malibu ES WFPD & HVAC Project (ES)
M | Modernization & HVAC | Window, Paint, Floor and Door & Fire Alarm, HVAC, ADA upgrades | Completed |  | 89522.66 | Malibu ES WFPD & HVAC Project (M) | In eBuilder but not in the original spreadsheet
ES | Malibu Alignment | Elementary Schools alignment & Playground Project | Completed | 5146835 | 2983729.85 | Malibu ES Schools Alignment (ES)
M | Malibu Alignment | Elementary Schools alignment & Playground Project | Completed |  | 6268314.19 | Malibu ES Schools Alignment (M) | In eBuilder but not in the original spreadsheet
M | Furniture, Fixtures & Equipment (FFE) | 21st century classroom furniture upgrade | Completed | 600000 | 770472.9 | Malibu ES FF&E Project (M)
M | Safety & Security | Adding cameras, raptor and other safety upgrades | Completed | 300000 | 512753.67 | Malibu ES Safety & Security Projects (M)
M | Safety & Security Project - PA/Clock Replacement Project | Adding cameras, raptor and other safety upgrades | Completed |  | 37443.11 | Malibu ES Safety & Security Project - PA/Clock Replacement Project (M) | In eBuilder but not in the original spreadsheet
M | Elementary School Campus Assessment | Elementary School Campus Assessment | Completed |  | 139625 | Malibu ES Elementary School Campus Assessment (M) | In eBuilder but not in the original spreadsheet
M | Alternative Power | Alternative Power | In Process |  | 420723.21 | Malibu ES Alternative Power Project (M) | In eBuilder but not in the original spreadsheet
Cabrillo Elementary School (now part of Malibu Middle/High School)
BB | Safety Project | Fence & Gate Safety & Security upgrades | Completed | 555604 |  |  | Not in eBuilder
ES | Modernization | Window, Paint, Floor and Door & ADA upgrades | Completed | 2216907 | 2214534.52 | Cabrillo ES WFPD Project (ES)
Malibu Middle/High School
BB & ES | Building AB/C Replacement & E Replacement | Construct New Library/Classroom/Admin Bldg & New Classroom Bldg | Completed | 97285142 |  |  | Not in eBuilder
BB | New Parking Lot | Construct 150 space parking lot | Completed | 0 |  |  | Not in eBuilder
BB | Off-Site Traffic | Required Traffic improvements offsite | Completed | 0 |  |  | Not in eBuilder
BB | Wastewater treatment | upgrades to septic and wastewater systems | Completed | 0 |  |  | Not in eBuilder
BB | Water District 29 | Water service upgrade (offsite package) | Completed | 462752 |  |  | Not in eBuilder
BB | Soil Remediation | Replace soil with PCBS | Completed | 426448 |  |  | Not in eBuilder
BB | Upgrade Fire Alarm | Replace & rewire fire alarm system | Completed | 2014274 |  |  | Not in eBuilder
ES | Safety & Security | Adding cameras, raptor and other safety upgrades | Completed | 5175 | 5175 | Malibu MHS Safety & Security Project (ES)
ES | HVAC & Electrical | HVAC & Electrical | Completed |  | 878159.8 | Malibu MHS HVAC & Electrical Project (ES) | In eBuilder but not in the original spreadsheet
M | HVAC & Electrical | HVAC & Electrical | Completed |  | 82436.66 | Malibu MHS HVAC & Electrical Project (M) | In eBuilder but not in the original spreadsheet
ES | Interior Light Fixture | Interior Light Fixture | Completed |  | 2170216.97 | Malibu MHS Interior Light Fixture (ES) | In eBuilder but not in the original spreadsheet
ES | Environmental Caulk Removal | Environmental Caulk Removal | Completed |  | 1624136.68 | Malibu MHS Environmental Caulk Removal (ES) | In eBuilder but not in the original spreadsheet
ES | Solar | Solar | Completed |  | 4000000 | Malibu MHS Solar Project - Alternative Energy (ES) | In eBuilder but not in the original spreadsheet
ES | WPFD | WPFD | Completed |  | 8445981.49 | Malibu MHS WPFD Project - BLDG D,F,G,H,I,J,K (ES) | In eBuilder but not in the original spreadsheet
M | WPFD | WPFD | Completed |  | 670958.23 | Malibu MHS WPFD Project - BLDG D,F,G,H,I,J,K (M) | In eBuilder but not in the original spreadsheet
ES | Cafetorium Improvement | Cafetorium Improvement | Completed |  | 301405.68 | Malibu MHS Cafetorium Improvement Project (ES) | In eBuilder but not in the original spreadsheet
ES | Malibu Alignment | Reorganization of Malibu schools | Completed | 2983730 |  |  | Not in eBuilder
M | Furniture, Fixtures & Equipment (FFE) | 21st century classroom furniture upgrade | Completed | 4600000 | 256934.07 | Malibu MHS FF&E Project (M)
M | Safety & Security | Adding cameras, raptor and other safety upgrades | Completed | 1800000 | 2440898.44 | Malibu MHS Safety & Security Project (M)
ES | Campus Plan | Campus Plan | Completed |  | 368245.74 | Malibu MHS Campus Plan (ES) | In eBuilder but not in the original spreadsheet
M | Malibu Campus Plan - Phase 1 | Master Planning Malibu MS/HS Campus Plan & construct Phase 1 | Completed | 157494600 | 8267686.88 | Malibu MHS Campus Plan (M)
M | Malibu Campus Plan - Phase 2 | Master Planning Malibu MS/HS Phase 2 (design only) | Completed | 4000000 | 7938619.27 | Malibu MHS Campus Plan Phase 2 (M)
ES | Interim Measures | Interim Measures, including required PCB abatement | Completed | 2000000 | 29243.76 | Malibu MHS Campus Plan - Interim Measures (ES)
M | Malibu Campus Plan Interim Measures | Modular Village Relocation | Completed | 968300 | 800452.07 | Malibu MHS Campus Plan - Interim Measures (M)
M | Bulding E and I-Art Program Relocation of Klin | Improvements to Bldg. E and I Art classrooms and Construction of new kiln enclosure | Completed | 1093565 |  |  | Not in eBuilder
M | New High School Building-Phase 1 | Construction of a new 75,0009 SF, 2-story high school building | Completed | 149500000 | 126356987.55 | Malibu MHS New High School Project (M)
M | Alternative Power |  |  |  | 1112185.33 | Malibu MHS Alternative Power (M) | In eBuilder but not in the original spreadsheet
M | New Middle School Recreation Center/MPR and Aquatices Facility | Construction of new middle school recreation center/MPR, innovation lab, kitchen, eating area, wellness center, life skills classrooms and new aquatic center (design only) | In Design | 4239000 |  |  | Not in eBuilder
MM | New Middle School Recreation Center/MPR and Aquatices Facility | Construction of new middle school recreation center/MPR, innovation lab, kitchen, eating area, wellness center, life skills classrooms and new aquatic center (construction only) | In Design |  |  |  | Not in eBuilder
TECHNOLOGY DISTRICTWIDE
BB | Data Center | Preliminary project | Completed | 75198 |  |  | Not in eBuilder
BB | Data Center Districtwide Technology | Construct and implement districtwide data center | Completed | 8280686 |  |  | Not in eBuilder
ES | 21st Century Classrooms | updates classrooms for 21st century technology | Completed | 10953440 | 11953435.93 | ED Services 21st Century Classrooms (ES)
ES | Computer Lab Upgrades | modernizes computer labs throughout district | Completed | 2511600 | 1349557.32 | ED Services Computer Lab Upgrades (ES)
ES | Infrastructure | updates technological backbone to IT operations | Completed | 10792103 | 12764131.42 | ED Services Infrastructure (ES)
ES | Leadership & Capacity Building | Professional Development training on new technology | Completed | 3384922 | 1359657.28 | ED Services Leadership & Capacity-Building (ES)
ES | Library | Library upgrades with 21st century tech | Completed | 2139738 | 589002.85 | ED Services Library (ES)
ES | SBAC & Initial 1-1 devices | devices for students | Completed | 4432555 | 5742323.25 | ED Services SBAC & Initial 1-1 Devices (ES)
School Site Technology
BB | Edison Technology | 21st Century technology upgrades | Completed | 156293 |  |  | Not in eBuilder
BB | Franklin Technology | 21st Century technology upgrades | Completed | 322805 |  |  | Not in eBuilder
BB | Grant Technology | 21st Century technology upgrades | Completed | 304739 |  |  | Not in eBuilder
BB | McKinley Technology | 21st Century technology upgrades | Completed | 247495 |  |  | Not in eBuilder
BB | Rogers Technology | 21st Century technology upgrades | Completed | 233720 |  |  | Not in eBuilder
BB | Roosevelt Technology | 21st Century technology upgrades | Completed | 295518 |  |  | Not in eBuilder
BB | Muir/SMASH Technology | 21st Century technology upgrades | Completed | 344847 |  |  | Not in eBuilder
BB | Webster Technology | 21st Century technology upgrades | Completed | 230307 |  |  | Not in eBuilder
BB | Malibu ES Technology | 21st Century technology upgrades | Completed | 259144 |  |  | Not in eBuilder
BB | Cabrillo Technology | 21st Century technology upgrades | Completed | 255267 |  |  | Not in eBuilder
BB | Adams Technology | 21st Century technology upgrades | Completed | 1024691 |  |  | Not in eBuilder
BB | Lincoln Technology | 21st Century technology upgrades | Completed | 1107591 |  |  | Not in eBuilder
BB | Obama Technology | 21st Century technology upgrades | Completed | 208196 |  |  | Not in eBuilder
BB | Malibu HS Technology | 21st Century technology upgrades | Completed | 757818 |  |  | Not in eBuilder
BB | Samohi Technology | 21st Century technology upgrades | Completed | 1486619 |  |  | Not in eBuilder
BB | Transportation Technology | 21st Century technology upgrades | Completed | 5588 |  |  | Not in eBuilder
BB | Washington Technology | 21st Century technology upgrades | Completed | 54356 |  |  | Not in eBuilder
Updated July 2024